## Sheet0
Jira.Project | Execution.Key | Execution.Assigned To | Execution.Type | Execution.Execution Date | Execution.Actual | Execution.Estimated | Execution.Result | Execution.Environment | Execution.Linked Issues | Execution.Count of Linked Issues | Test Cycle.Key | Test Cycle.Name | Test Cycle.Description | Test Cycle.Folder | Test Cycle.Status | Test Cycle.Version | Test Cycle.Owner | Test Cycle.Planned Start Date | Test Cycle.Planned End Date | Test Case.Key | Test Case.Name | Test Case.Component | Test Case.Owner | Test Case.Created By | Test Case.Created On | Test Case.Version | Test Case.Estimated | Test Case.Objective | Test Case.Precondition | Test Case.Status | Test Case.Folder | Test Case.Labels | Test Case.Priority | Test Case.Traceability.Issue | Test Case.Traceability.Weblink
SCRUM | SCRUM-E1 | saranteja vvds | MANUAL | 2025-02-17 | 00:02 | 00:05 | Pass |  |  | 0 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T1 | Validate Admin Login with Valid Data |  | saranteja vvds | saranteja vvds | 2025-02-09 | 1 | 00:05 | <strong>This Test Case validates Admin Login with Valid Data.</strong> |  | Draft | /Stock Accounting Admin Login |  | High | SCRUM-6
SCRUM | SCRUM-E2 | saranteja vvds | MANUAL | 2025-02-17 | 00:02 | 00:05 | Pass |  |  | 0 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T2 | Validate Admin Login with Invalid Data |  | saranteja vvds | saranteja vvds | 2025-02-09 | 1 | 00:05 | <strong>This Test Case validates Admin Login with Invalid Data.</strong> |  | Draft | /Stock Accounting Admin Login |  | High | SCRUM-7
SCRUM | SCRUM-E3 | saranteja vvds | MANUAL | 2025-02-17 | 00:04 | 00:05 | Pass |  |  | 0 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T3 | Validate hyperlinks on Stock Accounting Home Page. |  | saranteja vvds | saranteja vvds | 2025-02-09 | 1 | 00:05 | <strong>This Test Case validates all Hyperlinks on Stock Accounting Home Page.</strong> |  | Draft | /Stock Accounting Homepage |  | High | SCRUM-8
SCRUM | SCRUM-E4 | saranteja vvds | MANUAL | 2025-02-17 | 00:07 | 00:05 | Fail |  | SCRUM-24 | 1 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T4 | Validate Stock Items Details Page |  | saranteja vvds | saranteja vvds | 2025-02-09 | 1 | 00:05 | <strong>This Test Case validates Stock Items Details Page.</strong> |  | Draft | /Stock Items |  | High | SCRUM-9
SCRUM | SCRUM-E5 | saranteja vvds | MANUAL | 2025-02-18 | 00:05 | 00:05 | Pass |  |  | 0 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T5 | Validate Stock Item Creation with Valid Data |  | saranteja vvds | saranteja vvds | 2025-02-09 | 1 | 00:05 | <strong>This Test Case validates Stock Item Creation with Valid Data.</strong> |  | Draft | /Stock Items |  | High | SCRUM-10
SCRUM | SCRUM-E6 | saranteja vvds | MANUAL | 2025-02-18 | 00:03 | 00:05 | Fail |  | SCRUM-25,SCRUM-26,SCRUM-27 | 3 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T6 | Validate Stock Item Creation with Invalid Data |  | saranteja vvds | saranteja vvds | 2025-02-09 | 1 | 00:05 | <strong>This Test Case validates Stock Item Creation with Invalid Data.</strong> |  | Draft | /Stock Items |  | High | SCRUM-11
SCRUM | SCRUM-E7 | saranteja vvds | MANUAL | 2025-02-18 | 00:01 | 00:05 | Pass |  |  | 0 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T7 | Validate Stock Item Updation Page |  | saranteja vvds | saranteja vvds | 2025-02-09 | 1 | 00:05 | <strong>This Test Case validates Stock Item Updation Page.</strong> |  | Draft | /Stock Items |  | Normal | SCRUM-12
SCRUM | SCRUM-E8 | saranteja vvds | MANUAL | 2025-02-18 | 00:03 | 00:05 | Pass |  |  | 0 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T8 | Validate Stock Item Deletion Page |  | saranteja vvds | saranteja vvds | 2025-02-09 | 1 | 00:05 | <strong>This Test Case validates Stock Item Deletion &nbsp;Page.</strong> |  | Draft | /Stock Items |  | Normal | SCRUM-13
SCRUM | SCRUM-E9 | saranteja vvds | MANUAL | 2025-02-18 | 00:07 | 00:05 | Fail |  | SCRUM-28 | 1 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T9 | Validate Suppliers Details Page |  | saranteja vvds | saranteja vvds | 2025-02-13 | 1 | 00:05 | <strong>This Testcase validates Suppliers details page.</strong> |  | Draft | /Suppliers |  | High | SCRUM-14
SCRUM | SCRUM-E10 | saranteja vvds | MANUAL | 2025-02-18 | 00:03 | 00:05 | Pass |  |  | 0 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T10 | Validate Supplier Creation Page with Valid Data |  | saranteja vvds | saranteja vvds | 2025-02-13 | 1 | 00:05 | <strong id="isPasted">This Testcase validates Supplier Creation page with Valid Data.</strong> |  | Draft | /Suppliers |  | High | SCRUM-15
SCRUM | SCRUM-E11 | saranteja vvds | MANUAL | 2025-02-18 | 00:03 | 00:05 | Fail |  | SCRUM-29,SCRUM-30,SCRUM-31,SCRUM-32,SCRUM-33,SCRUM-34,SCRUM-35,SCRUM-36,SCRUM-37,SCRUM-38 | 10 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T11 | Validate Supplier Creation page with Invalid Data |  | saranteja vvds | saranteja vvds | 2025-02-13 | 1 | 00:05 | <strong id="isPasted">This Testcase validates Supplier<strong id="isPasted">&nbsp;Creation page with Invalid Data</strong>.</strong> |  | Draft | /Suppliers |  | High | SCRUM-16
SCRUM | SCRUM-E12 | saranteja vvds | MANUAL | 2025-02-18 | 00:01 | 00:05 | Pass |  |  | 0 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T12 | Validate Supplier Updation Page |  | saranteja vvds | saranteja vvds | 2025-02-13 | 1 | 00:05 | <strong>This Testcase validates Supplier Updation page.</strong> |  | Draft | /Suppliers |  | Normal | SCRUM-17
SCRUM | SCRUM-E13 | saranteja vvds | MANUAL | 2025-02-18 | 00:05 | 00:05 | Pass |  |  | 0 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T13 | Validate Supplier Deletion Page |  | saranteja vvds | saranteja vvds | 2025-02-16 | 1 | 00:05 | <strong>This Testcase validates Supplier Deletion page.</strong> |  | Draft | /Suppliers |  | Normal | SCRUM-18
SCRUM | SCRUM-E19 | saranteja vvds | MANUAL | 2025-02-18 | 00:05 | 00:05 | Fail |  | SCRUM-39 | 1 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T14 | Validate Customers Details Page |  | saranteja vvds | saranteja vvds | 2025-02-16 | 1 | 00:05 | <strong>This TestCase validates Customers Details Page.</strong> |  | Draft | /Customers |  | High | SCRUM-19
SCRUM | SCRUM-E20 | saranteja vvds | MANUAL | 2025-02-18 | 00:03 | 00:05 | Pass |  |  | 0 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T15 | Validate Customer Creation Page with Valid Data |  | saranteja vvds | saranteja vvds | 2025-02-16 | 1 | 00:05 | <strong>This TestCase validates Customer Creation Page with Valid Data.</strong> |  | Draft | /Customers |  | High | SCRUM-20
SCRUM | SCRUM-E21 | saranteja vvds | MANUAL | 2025-02-18 | 00:01 | 00:05 | Fail |  | SCRUM-40,SCRUM-41,SCRUM-42,SCRUM-43,SCRUM-44,SCRUM-45,SCRUM-46,SCRUM-47,SCRUM-48,SCRUM-49 | 10 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T16 | Validate Customer Creation Page with Invalid Data |  | saranteja vvds | saranteja vvds | 2025-02-16 | 1 | 00:05 | <strong>This TestCase validates Customer Creation Page with Invalid Data.</strong> |  | Draft | /Customers |  | High | SCRUM-21
SCRUM | SCRUM-E22 | saranteja vvds | MANUAL | 2025-02-18 | 00:01 | 00:05 | Pass |  |  | 0 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T17 | Validate Customer Updation Page |  | saranteja vvds | saranteja vvds | 2025-02-16 | 1 | 00:05 | <strong>This TestCase validates Customer Updation Page.</strong> |  | Draft | /Customers |  | Normal | SCRUM-22
SCRUM | SCRUM-E23 | saranteja vvds | MANUAL | 2025-02-18 | 00:02 | 00:05 | Pass |  |  | 0 | SCRUM-R1 | ERP_1 Regression Testing for Stock Accounting Project | <strong>Testing was done in Windows Chrome Browser.</strong> | /Regression_Testing_for_Stock_Accounting_Project | Done |  | saranteja vvds | 2025-02-16 | 2025-02-20 | SCRUM-T18 | Validate Customer Deletion Page |  | saranteja vvds | saranteja vvds | 2025-02-16 | 1 | 00:05 | <strong>This TestCase validates Customer Deletion Page.</strong> |  | Draft | /Customers |  | Normal | SCRUM-23